## Effort Summary
Project | Shopping Cart |  |  | Estimator | V.Thusyanthy
Project Type | Bench - Assignment |  |  | Reviewed by
Total Effort Estimation | 470 |  |  | Reviewed date
 | time axis 2020-06-01 to 2020-08-28
|  |  | Optimistic Effort P Hours | Most Likely Effort P Hours | Pessimistic Effort P Hours | Actual Effort | Plan Start Date | Plan End Date | Actual Start Date | Actual End Date | Status | 2020-06-01: Week 1; 2020-06-08: Week 2; 2020-06-15: Week 3; 2020-06-22: Week 4; 2020-06-29: Week 5; 2020-07-06: Week 6; 2020-07-13: Week 7; 2020-07-20: Week 8; 2020-07-27: Week 9; 2020-08-03: Week 10; 2020-08-10: Week 11; 2020-08-17: Week 12; 2020-08-24: Week 13
[12 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Login Page |  | 0 |  | 0 | 0
2 | Design | Design Development | 3 | 4 | 6 | 4 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 |  | Week 2 T: 4
3 | Design Review | Design Review | 1 | 1 | 2 | 1
4 | Design Rework | Design Rework | 1 | 1 | 2 | 1
5 | Data Access Layer Development | Code Development | 2 | 3 | 5 | 3 | 2020-06-16 | 2020-06-16 |  |  |  | Week 3 W: 1; Week 3 T: 2
6 | Business Layer Development | Code Development | 2 | 3 | 5 | 3 | 2020-06-23 | 2020-06-23 |  |  |  | Week 5 M: 3
7 | Service Layer Development | Code Development | 4 | 5 | 8 | 6 | 2020-06-25 | 2020-06-25 |  |  |  | Week 5 W: 5
8 | Web Client Development | Code Development | 5 | 6 | 9 | 7 | 2020-06-26 | 2020-06-26 |  |  |  | Week 5 T: 6
9 | Unit Test | Dev Testing | 2 | 2 | 3 | 2 | 2020-06-26 | 2020-06-29 | bar: Week 5 T to Week 5 F
10 | Code Review | Code Review | 1 | 1 | 2 | 1 | 2020-06-30 | 2020-06-30 | bar: Week 6 M
11 | Code Rework | Code Rework | 2 | 2 | 3 | 2 | 2020-06-30 | 2020-06-30 |  |  |  | Week 6 M: 2
12 |  |  | 0 |  | 0 | 0
13 | Customer Registration Page |  | 0 |  | 0 | 0
14 | Design | Design Development | 3 | 4 | 6 | 4 | 2020-06-10 | 2020-06-10 | 2020-06-10 | 2020-06-10 |  | Week 2 W: 4
15 | Design Review | Design Review | 1 | 1 | 2 | 1
16 | Design Rework | Design Rework | 1 | 1 | 2 | 1
17 | Data Access Layer Development | Code Development | 2 | 3 | 5 | 3 | 2020-06-17 | 2020-06-17 |  |  |  | Week 3 F: 3
18 | Business Layer Development | Code Development | 2 | 3 | 5 | 3 | 2020-06-24 | 2020-06-24 |  |  |  | Week 5 T: 3
19 | Service Layer Development | Code Development | 2 | 2 | 3 | 2 | 2020-06-25 | 2020-06-25 |  |  |  | Week 5 W: 2
20 | Web Client Development | Code Development | 3 | 4 | 6 | 4 | 2020-06-29 | 2020-06-29 |  |  |  | Week 5 F: 4
21 | Unit Test | Dev Testing | 2 | 2 | 3 | 2 | 2020-06-29 | 2020-06-29 |  |  |  | Week 5 F: 2
22 | Code Review | Code Review | 1 | 1 | 2 | 1 | 2020-07-01 | 2020-07-01 | bar: Week 6 T
23 | Code Rework | Code Rework | 2 | 2 | 3 | 2 | 2020-07-01 | 2020-07-01 |  |  |  | Week 6 T: 2
24 |  |  | 0 |  | 0 | 0
25 | Product List Page |  | 0 |  | 0 | 0
26 | Design | Design Development | 5 | 6 | 9 | 7 | 2020-06-11 | 2020-06-12 | 2020-06-11 | 2020-06-12 |  | Week 2 T: 5; Week 2 F: 1
27 | Design Review | Design Review | 1 | 1 | 2 | 1
28 | Design Rework | Design Rework | 2 | 2 | 3 | 2
29 | Data Access Layer Development | Code Development | 6 | 8 | 12 | 9 | 2020-06-23 | 2020-06-25 |  |  |  | Week 4 T: 2; Week 4 W: 4; Week 4 T: 2
30 | Business Layer Development | Code Development | 6 | 8 | 12 | 9 | 2020-06-30 | 2020-07-01 |  |  |  | Week 6 M: 4; Week 6 T: 4
31 | Service Layer Development | Code Development | 5 | 6 | 9 | 7 | 2020-07-02 | 2020-07-02 |  |  |  | Week 6 W: 6
32 | Web Client Development | Code Development | 15 | 20 | 30 | 22 | 2020-07-03 | 2020-07-08 |  |  |  | Week 6 T: 5; Week 6 F: 7; Week 7 M: 7; Week 7 T: 1
33 | Unit Test | Dev Testing | 3 | 4 | 6 | 4 | 2020-07-08 | 2020-07-08 |  |  |  | Week 7 T: 4
34 | Code Review | Code Review | 2 | 2 | 3 | 2 | 2020-07-09 | 2020-07-09 |  |  |  | Week 7 W: 2
35 | Code Rework | Code Rework | 3 | 4 | 6 | 4 | 2020-07-09 | 2020-07-09 |  |  |  | Week 7 W: 4
36 |  |  | 0 |  | 0 | 0
37 | Product Cart Page |  | 0 |  | 0 | 0
38 | Design | Design Development | 2 | 3 | 5 | 3 | 2020-06-12 | 2020-06-15 | 2020-06-12 | 2020-06-15 |  | Week 2 F: 2; Week 3 M: 1
39 | Design Review | Design Review | 1 | 1 | 2 | 1
40 | Design Rework | Design Rework | 1 | 1 | 2 | 1
41 | Data Access Layer Development | Code Development | 2 | 3 | 5 | 3 | 2020-06-18 | 2020-06-18 |  |  |  | Week 3 T: 2; Week 3 F: 1
42 | Business Layer Development | Code Development | 2 | 3 | 5 | 3 | 2020-07-02 | 2020-07-03 |  |  |  | Week 6 W: 1; Week 6 T: 2
43 | Service Layer Development | Code Development | 2 | 3 | 5 | 3 | 2020-07-08 | 2020-07-09 |  |  |  | Week 7 T: 2; Week 7 W: 1
44 | Web Client Development | Code Development | 5 | 7 | 11 | 8 | 2020-07-10 | 2020-07-10 |  |  |  | Week 7 T: 7
45 | Unit Test | Dev Testing | 2 | 2 | 3 | 2 | 2020-07-13 | 2020-07-13 |  |  |  | Week 7 F: 2
46 | Code Review | Code Review | 1 | 1 | 2 | 1 | 2020-07-13 | 2020-07-13 | bar: Week 7 F
47 | Code Rework | Code Rework | 2 | 2 | 3 | 2 | 2020-07-13 | 2020-07-13 |  |  |  | Week 7 F: 2
48 |  |  | 0 |  | 0 | 0
49 | Checkout Page |  | 0 | 0 | 0 | 0
50 | Design | Design Development | 3 | 4 | 6 | 4 | 2020-06-12 | 2020-06-12 | 2020-06-12 | 2020-06-12 |  | Week 2 F: 4
51 | Design Review | Design Review | 1 | 1 | 2 | 1
52 | Design Rework | Design Rework | 1 | 1 | 2 | 1
53 | Data Access Layer Development | Code Development | 3 | 4 | 6 | 4 | 2020-06-19 | 2020-06-19 |  |  |  | Week 4 M: 4
54 | Business Layer Development | Code Development | 3 | 4 | 6 | 4 | 2020-07-13 | 2020-07-14 |  |  |  | Week 7 F: 2; Week 8 M: 2
55 | Service Layer Development | Code Development | 2 | 3 | 5 | 3 | 2020-07-14 | 2020-07-14 |  |  |  | Week 8 M: 3
56 | Web Client Development | Code Development | 5 | 7 | 11 | 8 | 2020-07-14 | 2020-07-15 |  |  |  | Week 8 M: 2; Week 8 T: 5
57 | Unit Test | Dev Testing | 2 | 2 | 3 | 2 | 2020-07-15 | 2020-07-15 |  |  |  | Week 8 T: 2
58 | Code Review | Code Review | 2 | 2 | 3 | 2 | 2020-07-16 | 2020-07-16 |  |  |  | Week 8 W: 2
59 | Code Rework | Code Rework | 2 | 3 | 5 | 3 | 2020-07-16 | 2020-07-16 |  |  |  | Week 8 W: 3
60 |  |  | 0 |  | 0 | 0
61 | Payment Confirmation Page |  | 0 | 0 | 0 | 0
62 | Design | Design Development | 2 | 3 | 5 | 3 | 2020-06-15 | 2020-06-15 | 2020-06-15 | 2020-06-15 |  | Week 3 M: 3
63 | Design Review | Design Review | 1 | 1 | 2 | 1
64 | Design Rework | Design Rework | 1 | 1 | 2 | 1
65 | Data Access Layer Development | Code Development | 3 | 4 | 6 | 4 | 2020-06-22 | 2020-06-22 |  |  |  | Week 4 F: 4
66 | Business Layer Development | Code Development | 3 | 4 | 6 | 4 | 2020-07-16 | 2020-07-17 |  |  |  | Week 8 W: 2; Week 8 T: 2
67 | Service Layer Development | Code Development | 2 | 2 | 3 | 2 | 2020-07-17 | 2020-07-17 |  |  |  | Week 8 T: 2
68 | Web Client Development | Code Development | 5 | 6 | 9 | 7 | 2020-07-17 | 2020-07-20 |  |  |  | Week 8 T: 3; Week 8 F: 3
69 | Unit Test | Dev Testing | 1 | 2 | 3 | 2 | 2020-07-20 | 2020-07-20 |  |  |  | Week 8 F: 2
70 | Code Review | Code Review | 1 | 2 | 3 | 2 | 2020-07-21 | 2020-07-21 |  |  |  | Week 9 M: 2
71 | Code Rework | Code Rework | 1 | 2 | 3 | 2 | 2020-07-21 | 2020-07-21 |  |  |  | Week 9 M: 2
72 |  |  | 0 |  | 0 | 0
73 | Order Details Page |  | 0 |  | 0 | 0
74 | Design | Design Development | 2 | 3 | 5 | 3 | 2020-06-17 | 2020-06-17 |  |  |  | Week 3 W: 3
75 | Design Review | Design Review | 1 | 1 | 2 | 1
76 | Design Rework | Design Rework | 1 | 1 | 2 | 1
77 | Data Access Layer Development | Code Development | 3 | 4 | 6 | 4 | 2020-06-23 | 2020-06-23 |  |  |  | Week 5 M: 4
78 | Business Layer Development | Code Development | 3 | 4 | 6 | 4 | 2020-07-20 | 2020-07-21 |  |  |  | Week 8 F: 2; Week 9 M: 2
79 | Service Layer Development | Code Development | 2 | 3 | 5 | 3 | 2020-07-21 | 2020-07-22 |  |  |  | Week 9 M: 1; Week 9 T: 2
80 | Web Client Development | Code Development | 5 | 6 | 9 | 7 | 2020-07-22 | 2020-07-23 |  |  |  | Week 9 T: 5; Week 9 W: 1
81 | Unit Test | Dev Testing | 1 | 2 | 3 | 2 | 2020-07-23 | 2020-07-23 |  |  |  | Week 9 W: 2
82 | Code Review | Code Review | 1 | 2 | 3 | 2 | 2020-07-24 | 2020-07-24 |  |  |  | Week 9 T: 2
83 | Code Rework | Code Rework | 4 | 2 | 3 | 3 | 2020-07-24 | 2020-07-24 |  |  |  | Week 9 T: 2
84 |  |  | 0 |  | 0 | 0
85 | Payment History Page |  | 0 |  | 0 | 0
86 | Design | Design Development | 3 | 4 | 6 | 4 | 2020-06-16 | 2020-06-16 |  |  |  | Week 3 T: 4
87 | Design Review | Design Review | 1 | 1 | 2 | 1
88 | Design Rework | Design Rework | 1 | 1 | 2 | 1
89 | Data Access Layer Development | Code Development | 3 | 4 | 6 | 4 | 2020-06-24 | 2020-06-24 |  |  |  | Week 5 T: 4
90 | Business Layer Development | Code Development | 3 | 4 | 6 | 4 | 2020-07-23 | 2020-07-23 |  |  |  | Week 9 W: 4
91 | Service Layer Development | Code Development | 2 | 2 | 3 | 2 | 2020-07-24 | 2020-07-24 |  |  |  | Week 9 T: 2
92 | Web Client Development | Code Development | 5 | 6 | 9 | 7 | 2020-07-24 | 2020-07-24 |  |  |  | Week 9 T: 1; Week 9 F: 5
93 | Unit Test | Dev Testing | 2 | 2 | 3 | 2 | 2020-07-27 | 2020-07-27 |  |  |  | Week 9 F: 2
94 | Code Review | Code Review | 1 | 1 | 2 | 1 | 2020-07-28 | 2020-07-28 | bar: Week 10 T
95 | Code Rework | Code Rework | 2 | 2 | 3 | 2 | 2020-07-28 | 2020-07-28 |  |  |  | Week 10 T: 2
96
97 | Email Notification |  | 0 |  | 0 | 0
98 | Design | Design Development | 2 | 2 | 3 | 2 | 2020-06-22 | 2020-06-22 |  |  |  | Week 4 T: 2
99 | Design Review | Design Review | 1 | 1 | 2 | 1
100 | Design Rework | Design Rework | 1 | 1 | 2 | 1
101 | Functionality Development | Code Development | 7 | 9 | 14 | 10 | 2020-07-28 | 2020-07-29 |  |  |  | Week 10 T: 4; Week 10 W: 5
102 | Unit Test | Dev Testing | 2 | 2 | 3 | 2 | 2020-07-29 | 2020-07-29 |  |  |  | Week 10 W: 2
103 | Code Review | Code Review | 2 | 2 | 3 | 2 | 2020-07-30 | 2020-07-30 |  |  |  | Week 10 T: 2
104 | Code Rework | Code Rework | 2 | 2 | 3 | 2 | 2020-07-30 | 2020-07-30 |  |  |  | Week 10 T: 2
105 |  |  | 0 |  | 0 | 0
106 | Database Development |  | 0 |  | 0 | 0
107 | Design | Design Development | 5 | 7 | 11 | 8 | 2020-06-08 | 2020-06-08 | 2020-06-08 | 2020-06-08 |  | Week 2 M: 7
108 | Design Review | Design Review | 2 | 2 | 3 | 2
109 | Design Rework | Design Rework | 2 | 2 | 3 | 2
110 | Database Development | Code Development | 6 | 8 | 12 | 9 | 2020-06-09 | 2020-06-11 | 2020-06-09 | 2020-06-11 |  | Week 2 T: 3; Week 2 W: 3; Week 2 T: 2
111 | Database Development Review | Design Review | 2 | 2 | 3 | 2
112 | Database Development Rework | Design Rework | 2 | 2 | 3 | 2
113 | Data Feed | Code Development | 2 | 2 | 3 | 2 | 2020-06-15 | 2020-06-15 |  |  |  | Week 4 T: 2
114 |  |  | 0 |  | 0 | 0
115 | General/Miscellaneous |  | 0 |  | 0 | 0
116 | Environment Setup | Project Planning | 6 | 8 | 12 | 9 | 2020-06-02 | 2020-06-03 | 2020-06-02 | 2020-06-03 |  | Week 1 T: 1; Week 1 W: 7
117 | Requirement Analyze | Requirements Dev | 5 | 6 | 9 | 7 | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02 |  | Week 1 T: 6
118 | Requirement Review | Requirements Review | 2 | 2 | 3 | 2 | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02
119 | Project Structure and Design | Code Development | 5 | 7 | 11 | 8 | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-04 |  | Week 1 T: 7
120 | Database Integration Using EF | Code Development | 24 | 32 | 48 | 35 | 2020-08-04 | 2020-08-10 |  |  |  | Week 11 M: 7; Week 11 T: 7; Week 11 W: 7; Week 11 T: 7; Week 11 F: 4
121 | Logging | Code Development | 12 | 16 | 24 | 17 | 2020-08-14 | 2020-08-18 |  |  |  | Week 12 T: 7; Week 12 F: 7; Week 13 M: 2
122 | Exception | Code Development | 12 | 16 | 24 | 17 | 2020-08-11 | 2020-08-12 |  |  |  | Week 12 M: 2; Week 12 T: 7; Week 12 W: 7
123 | E2E testing | Dev Testing | 8 | 10 | 15 | 11 | 2020-07-30 | 2020-07-31 |  |  |  | Week 10 T: 3; Week 10 F: 7
124 | Regrestion Testing afyter integrate EF |  | 6 | 8 | 12 | 9 | 2020-08-10 | 2020-08-11 |  |  |  | Week 11 F: 3; Week 12 M: 5
125 |  |  | 0 |  | 0 | 0
126 | Meeting |  | 0 |  | 0 | 0
127 | Meeting and Handovers |  | 30 | 40 | 60 | 43 | 2020-06-02 | 2020-08-31 | 2020-06-02 | 2020-08-31 | bar: Week 1 T to Week 1 T; Week 2 M to Week 9 F; Week 10 T to Week 13 F
128 |  |  | 0 |  | 0 | 0
129 | MicroServices Session |  | 0 |  | 0 | 0 | [5 empty] | Week 3 M: 3; Week 3 T: 3; Week 3 W: 3; Week 3 T: 3; Week 3 F: 3; Week 4 M: 3; Week 4 T: 3; Week 4 W: 3; Week 4 T: 3; Week 4 F: 3
130 |  |  | 0
131 |  |  | 0 |  | 0 | 0
< End of Data > | [11 empty] | 0 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 3 | 1 | 1 | 1 | 1

## Sheet1
| API | Client
Login with credentials
User create

## Assumptions
Assumptions (List out all assumptions related to the estimates)
Please Note: All kinds of assumptions that have an impact on the project estimates and project schedule should be documented and their corresponding impact assessed and aligned to the estimate
Re-use Related Assumptions |  | 0 | Assumptions
No. | Description
1
2
3
4
5
6
7
8
9
Scope Related Assumptions |  | 0 | Assumptions
No. | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
Technical Assumptions |  | 0 | Assumptions
No. | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
Environment Related Assumptions |  | 0 | Assumptions
No. | Description
1
2
3
4
5
6
7
8
9
10
Team and Skill Related Assumptions |  | 0 | Assumptions
No. | Description
1
2
3
4
5
6
7
8
9
10
General Assumptions |  | 0 | Assumptions
No. | Description
1
2
3
4
5
6
7
8
9
10