## Sheet1
No | Task | Start Date | Due Date | End Date | Planned Effort | Actual effort | Task Complete(%) | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10
[8 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Requirement Gathering |  |  |  | 4hr
2
2.1 | Feasibility Study |  |  |  | 6hr
2.2 | Finalizing Technologies |  |  |  | 2hr
3 | Envirnment setup |  |  |  | 8hr
4 | Analyse Design
4.1 | Use Case |  |  |  | 2hr
4.2 | Sequence diagram |  |  |  | 3hr
4.3 | DataBase Design
4.3.1 | ER Diagram |  |  |  | 2hr
4.3.2 | Normalaization |  |  |  | 2hr
4.4 | Prepare API Documentation |  |  |  | 5hr
4.5 | Review and finalize the design |  |  |  | 2r
4.6 | Rework Design |  |  |  | 2hr
5 | Implement Databse
5.1 | Design Shcemas |  |  |  | 8hr
5.2 | Feeding Dummy Data |  |  |  | 2hr
6 | Implement API
6.1 | API - 01
6.1.1 | Development |  |  |  | 3hr
6.1.2 | Dev Testing |  |  |  | 0.5hr
6.1.3 | Unit Testing |  |  |  | 1hr
6.1.4 | Rework and Bug Fixing |  |  |  | 1hr
6.2 | API - 02
6.2.1 | Development |  |  |  | 2hr
6.2.2 | Dev Testing |  |  |  | 0.5hr
6.2.3 | Unit Testing |  |  |  | 1hr
6.2.4 | Rework and Bug Fixing |  |  |  | 1hr
6.3 | API - 03
6.3.1 | Development |  |  |  | 2hr
6.3.2 | Dev Testing |  |  |  | 0.5hr
6.3.3 | Unit Testing |  |  |  | 1hr
6.3.4 | Rework and Bug Fixing |  |  |  | 1hr
6.4 | API - 04
6.4.1 | Development |  |  |  | 6hr
6.4.2 | Dev Testing |  |  |  | 2hr
6.4.3 | Unit Testing |  |  |  | 2hr
6.4.4 | Rework and Bug Fixing |  |  |  | 1hr
6.5 | API - 05
6.5.1 | Development |  |  |  | 4hr
6.5.2 | Dev Testing |  |  |  | 0.5hr
6.5.3 | Unit Testing |  |  |  | 1hr
6.5.4 | Rework and Bug Fixing |  |  |  | 1hr
6.6 | API - 06
6.6.1 | Development |  |  |  | 3hr
6.6.2 | Dev Testing |  |  |  | 0.5hr
6.6.3 | Unit Testing |  |  |  | 1hr
6.6.4 | Rework and Bug Fixing |  |  |  | 1hr
6.7 | API - 07
6.7.1 | Development |  |  |  | 2hr
6.7.2 | Dev Testing |  |  |  | 0.5hr
6.7.3 | Unit Testing |  |  |  | 1hr
6.7.4 | Rework and Bug Fixing |  |  |  | 1hr
6.8 | API - 08
6.8.1 | Development |  |  |  | 3hr
6.8.2 | Dev Testing |  |  |  | 1hr
6.8.3 | Unit Testing |  |  |  | 1hr
6.8.4 | Rework and Bug Fixing |  |  |  | 1hr
6.9 | API - 09
6.9.1 | Development |  |  |  | 3hr
6.9.2 | Dev Testing |  |  |  | 1hr
6.9.3 | Unit Testing |  |  |  | 1hr
6.9.4 | Rework and Bug Fixing |  |  |  | 1hr
6.10 | API - 10
6.10.1 | Development |  |  |  | 4hr
6.10.2 | Dev Testing |  |  |  | 1hr
6.10.3 | Unit Testing |  |  |  | 1hr
6.10.4 | Rework and Bug Fixing |  |  |  | 1hr
6.11 | API - 11
6.11.1 | Development |  |  |  | 3hr
6.11.2 | Dev Testing |  |  |  | 1hr
6.11.3 | Unit Testing |  |  |  | 1hr
6.11.4 | Rework and Bug Fixing |  |  |  | 1hr
6.12 | API - 12
6.12.1 | Development |  |  |  | 3hr
6.12.2 | Dev Testing |  |  |  | 1hr
6.12.3 | Unit Testing |  |  |  | 1hr
6.12.4 | Rework and Bug Fixing |  |  |  | 1hr
6.13 | API - 13
6.13.1 | Development |  |  |  | 3hr
6.13.2 | Dev Testing |  |  |  | 1hr
6.13.3 | Unit Testing |  |  |  | 1hr
6.13.4 | Rework and Bug Fixing |  |  |  | 1hr
6.14 | API - 14
6.14.1 | Development |  |  |  | 3hr
6.14.2 | Dev Testing |  |  |  | 1hr
6.14.3 | Unit Testing |  |  |  | 1hr
6.14.4 | Rework and Bug Fixing |  |  |  | 1hr
6.15 | API - 15
6.15.1 | Development |  |  |  | 2hr
6.15.2 | Dev Testing |  |  |  | 0.5hr
6.15.3 | Unit Testing |  |  |  | 1hr
6.15.4 | Rework and Bug Fixing |  |  |  | 1hr
7 | Implement Front-End and Intregate services
7.1 | Module - 01
7.1.1 | Front-End Development
7.1.2 | Intregrate Service
7.1.3 | Dev Testing
7.1.4 | Unit Testing
7.1.5 | Rework and Bug Fixing
7.2 | Module - 02
7.2.1 | Front-End Development
7.2.2 | Intregrate Service
7.2.3 | Dev Testing
7.2.4 | Unit Testing
7.2.5 | Rework and Bug Fixing
7.3 | Module - 03
7.3.1 | Front-End Development
7.3.2 | Intregrate Service
7.3.3 | Dev Testing
7.3.4 | Unit Testing
7.3.5 | Rework and Bug Fixing

## Sheet2
Code | Descriiption | Method | EndPonit | Request | Response
API - 01 | Create User | Post | /user
API - 02 | Change Password | Put | /user
API - 03 | Forget Password
API - 04 | Login | Post | /user
API - 05 | Register customer | Post | /customer
API - 06 | Add Product | Post | /product
API - 07 | Update product | put | /product
API - 08 | Retrive Product | get | /product
API - 09 | Retrive Product by ID | get | /product/{id}
API - 10 | Retrive Product by Categary | get | /product/{categary}
API - 11 | Add Cart | post | /cart
API - 12 | Update Cart | put | /cart
API - 13 | Delete Cart | Delete | /cart
API - 14 | Retrive Cart | get | /cart
API - 15 | Order History | get | /order